Project Guideline

Objective: Analyze the different behavior modes of human and computer. Analyze how human is perceiving a game, and how computer is perceiving a game due to the difference in their situation when they are playing.

- Analyze the riskiness of a move made by human players. This can be identified by the follow ways:

  - Attacking (over pushing)

  - Involving in worse positions for some of “good” canadiates played by opponent

  - Complex positions turning

  - Rejecting easy draws and trades

- Identify the environment (must-win situation, player’s strength difference, opening choices, player’s own style, white or black) that causes the players to do such risky moves.

- Analyze computer’s risky moves against other players (expected to be low, and to be the same when they encountered different environments)

- Identify the environment (must-win situation, player’s strength difference, opening choices, player’s own style) that causes the computer to do such risky moves.

### **Week 1-2: Research and Planning**

**Goal**: Define the scope of the project, select chess games to analyze, and familiarize yourself with the tools.

**Tasks**:

- Research famous chess games with creative human moves (e.g., Kasparov vs. Topalov, 1999).

- Select 1-2 games to focus on for the project.

- Familiarize yourself with the `c` library and Stockfish.

- Plan the structure of your report and visualizations.

**Deliverables**:

- List of selected chess games.

- Outline of the report structure.

---

### **Week 3-4: Data Collection and Basic Analysis**

**Goal**: Load the selected chess games into Python and analyze key positions with Stockfish. Identify the situation where the game is played to give insight on the moves that were played.

**Tasks**:

- Use `python-chess` to load the selected games and extract move data.

- Identify key moments in the games where human players made creative or intuitive moves.

- Run Stockfish analysis on these positions to compare human moves with AI recommendations.

-Research the background of the match, identify key factors such as player’s strength and the score

**Deliverables**:

- Python code for loading and analyzing chess games.

- List of key positions and Stockfish’s recommended moves.

---

### **Week 5-6: Visualization Development**

**Goal**: Create visualizations to compare human and AI moves. Calculate the riskiness of each move made by human and made by computer.

**Tasks**:

- Use `matplotlib` or `plotly` to create annotated chessboards.

- Highlight key differences between human and AI moves (e.g., using arrows or color-coding).

- Save the visualizations as images or interactive plots.

-Develop a model that analyze the risk of each move

**Deliverables**:

- Annotated chessboard visualizations for key positions.

- Python code for generating visualizations.

---

### **Week 7-8: Narrative Writing**

**Goal**: Write narratives explaining the humanistic aspects of the human moves.

**Tasks**:

- Write short explanations for each key moment, focusing on the creativity, intuition, or emotion behind the human moves.

- Compare these explanations to Stockfish’s recommendations and explain why the AI chose differently.

- Refine the narratives to make them clear and engaging for a non-technical audience.

**Deliverables**:

- Written narratives for each key moment.

- Comparison of human vs. AI moves in narrative form.

---

### **Week 9-10: Interactive Report Drafting**

**Goal**: Draft the report, incorporating interactions, visualizations and narratives for audience.

**Tasks**:

- Insert the annotated chessboard visualizations and narratives into the report.

-Provide interaction interface to visualize the results in forms of heat map and line graphs

- Ensure the report is well-organized and easy to follow.

**Deliverables**:

- First draft of the interactive report.

---

### **Week 11-12: Final Touches and Polish**

**Goal**: Finish on the website and check the webpage for bugs

**Tasks**:

- Finish the website for the users to interact on

- Test the visualizations and ensure they are clear and accurate.

- Test the interactions such that it works well

**Deliverables**:

- Final polished webpage